## Chartt summary
Charity Digital Platform Development
ID | Task Name | Start Date | Duration | End Date | Dependencies
1 | Project Initiation | 2023-07-08 | 3 days
- Define project scope and objectives
- Identify stakeholders and team members
- Set up project communication channels
2 | Research and Requirements Gathering |  | 3 days |  | Task 1
- Research existing charity apps
- Gather user requirements and features
- Identify integration APIs (MTN, Airtel, Google Maps)
3 | System Design and Architecture |  | 2 days |  | Task 2
- Design app architecture and database schema
- Plan integration with MTN and Airtel APIs
- Plan Google Maps integration
4 | UI/UX Design |  | 5 days |  | Task 3
- Design user interfaces for mobile app
- Create wireframes and prototypes
- Gather user feedback for improvements
5 | Development |  | 8 days |  | Task 3, 4
- Develop frontend interfaces and user flows
- Implement API integrations (MTN, Airtel, Google Maps)
- Build campaign creation and management features
6 | Testing and Quality Assurance |  | 3 days |  | Task 5
- Conduct functional and integration testing
- Identify and fix bugs and issues
- Optimize app performance and security
7 | User Testing and Feedback |  | 2 days |  | Task 6
- Invite users to test the app
- Gather feedback and suggestions
- Implement necessary changes based on feedback
8 | Deployment and Launch |  | 2 days |  | Task 7
- Prepare for app deployment on app stores
- Create marketing materials and campaigns
- Launch the Charify app to the public
9 | Post-Launch Monitoring and Maintenance |  | on-going |  | Task 8
- Monitor app performance and user feedback
- Provide updates and enhancements as needed
- Ensure smooth operation of integrated APIs

## Gantt chart
Gantt Chart for Charify Mobile App Development
ID | Task Name | Start Date | Duration | End Date | Dependencies | 2023-07-10 | [14 empty] | 2023-08-01
[6 empty] | week 1 |  |  |  |  | week 2 |  |  |  |  | week 3 |  |  |  |  | week 4 |  |  |  |  | week 5 |  |  |  |  | week 6
[6 empty] | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18
1 | Project Initiation | 2023-07-08 | 3 day
2 | Research and Requirements Gathering |  | 3 days |  | Task 1
3 | System Design and Architecture |  | 2days |  | Task 2
4 | UI/UX Design |  | 5days |  | Task 3
5 | Development |  | 10 days |  | Task 3, 4
6 | Testing and Quality Assurance |  | 3 days |  | Task 5
7 | User Testing and Feedback |  | 5days |  | Task 6, 5
8 | Deployment and Launch |  | 2 days |  | Task 7
9 | Post-Launch Monitoring and Maintenance |  | on-going |  | Task 8